## OH Program Devel Timeline
| Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| PLANNING |  |  | ACTIVE SITE WORK
Meet with Program Leadership
Conduct Readiness Assessment
Conduct Oral Health Information Technology Assessment
Assess Care Coordination Capabilities/Dental Referral Network
Conduct Kickoff Meeting
Conduct Workflow Optimization Mapping
Conduct Workflow Mapping Follow-up Activities
Complete task list
Plan future state pilot test
Test future state
Implementation of Pilot Test
Review pilot test and run charts
Review progress and metrics
Conduct biweekly or monthly check-in calls/meetings
Referral Management
Agree on dental referral criteria
Identify referral options
Conduct referral mapping to develop internal workflow process
Develop referral agreements
Develop mechanism for bidirectional information exchange
Develop referral tracking process
Implement referral management strategy for oral health
Reporting
Prioritize reports of defined metrics
Work with leadership and HIT team to develop high-priority reports
Work with database analyst to write and validate reports
Review reports internally monthly
Develop Spread Plan
Implement spread plan
Create OH Implementation Summary Report, as needed
The above example of an oral health implementation project calendar assumes a total program development time of 15 months, which includes time needed for initial planning, piloting implementation with time for process improvement PDSA cycles, and implementation of the plan to spread to additional patient populations, care teams and/or practice sites. This example timeline can be adjusted based upon individual practice considerations.